## Sheet1
|  | Basin | ASSAM_ARAKAN
|  | Rig | RIG_X
|  | Location | LOC_ALPHA | Well: WELL_A
|  | Target (m) | 3850
|  | Installation Manager | ENG_ALPHA
Operation Date | 2026-09-24 | Rig Release from last LOC: LOC-P0 |  | Spud-in Date | 2026-07-12
Present Depth (M) | 2145 | Casing Details
24 hrs Progress (M) | 76 | Size (inch) | Casing Type | Shoe at (M) | FC at (M)
Present Operation | DRILLING
Operation days (Planned/actual) | 45/42
ILM days (planned/actual) | 0/0
Hole Size | 8.5 in
Operation Details
Drilling 8-1/2" hole section through Formation Alpha from 2,069m to 2,145m with controlled ROP. All parameters normal.
Bit Details
Bit Srl No. | SN-9428B | Type & Nozzle Size | PDC 3x16 | Make/IADC | M-516
Drilling Mtrs (24 hrs) | 76 | Drilling Mtrs (Cum) | 580 | Pulled out Bit Condition
Bit Hrs (24 hrs) | 18.5 | Bit Hrs (Cum) | 62.0
Mud Parameters |  |  |  | Solid Control Equipment
Mud Wt. (ppg) | 10.2 | Solid %( V/V) | 6 |  | Running Hrs
Viscosity (Sec/qt) | 48 | PV(Cps)/YP(Lbs/100 sqft) | 16/22 | Shale Shaker
Fluid Loss(cc/30min) | 6 | Gel 0/Gel10 (Lbs./100 Sq.ft) | 4/12 | Mud Cleaner
PH | 9.5 | Salinity(mg/ltr) | 1800 | Formation Top(m) | 2080
BHA Length (m) | 185 | BHA Weight (T) | 28
Formation Drilled | FORMATION_ALPHA
Bit Hydraulics
HHP (Bit) | 420 | Jet Velocity:(ft./sec) | 340 | Bit Efficiency (%) | 65
HHP (Total) | 650 | Annular Velocity (DC-OH)(ft./min) | 180 | Annular Velocity (DP-OH)(ft./min) | 120
Drilling Parameters
WOB (T) | 12 | Torque (On Bottom) (ft-lb) | 11000 | GPM | 550
RPM | 120 | Torque (Off Bottom) (ft-lb) | 4500 | SPP (psi) | 2800
Time Lost due to Shut Down
Hrs Lost: 2.5 | Reason: Scheduled pump liner inspection
NEXT OPERATION
Continue drilling 8-1/2" hole to 2,250m MD; monitor for formation transition.
Time B/up
| (hrs) |  | (hrs) |  | (hrs)
Operating Time | 21.5 | Force Majeure Time | 0.0 | Repairing Time | 2.5
Standby Day Time | 0.0 | Non Operating Time | 0.0 | ILM Time | 0.0
Remarks
Daily operations conducted safely. Parameter trend stable.
NPT in 24 hrs: 2.5 hrs, Cumm monthly NPT: 14.0 hrs